## Sheet1
Task #NO | Name | Assignment | Public/Private | Use Case | Time (days) | Budget
1 | Design Master Page | Frontend | Public | Homepage / Dashboard | 5 | -
2 | Crypto Price Widget | Frontend | Public | Live Coin Prices Display | 3 | 35$
3 | Floating Particles & UI FX | Frontend | Public | Visual Effects | 2 | 2$
4 | Random Trader Quotes | Frontend | Public | Motivation / UX | 1 | -
5 | Test with real user | Frontend | Public | Get real user experience | 1 | -
6 | Portfolio CRUD API | Backend | Private | Save / Update / View Portfolio | 3 | -
7 | PDF Portfolio Report | Backend | Private | Generate User Report | 3 | -
8 | Database Setup | Backend | Private | Store Portfolio & Quotes | 2 | 10$
9 | API Integration / Testing | Backend | Private | Connect Frontend & Backend | 3 | -
10 | UI Testing & Debugging | Frontend | Public | Ensure UX / Fix Bugs | 2 | -